## Work Plan
2023 GRI Reporting Project Plan
Note that this plan excludes stakeholder engagement and materiality assessment, which should be managed separately and completed in advance of preparing your GRI report. Add external verification if your company plans to pursue it. |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August
Task | Responsible Person(s) | Status | 10-14 | 17-21 | 24-28 | 31-4 | 7-11 | 14-18 | 21-25 | 28-4 | 7-11 | 14-18 | 21-25 | 28-1 | 4-8 | 11-15 | 18-22 | 25-29 | 2-6 | 9-13 | 16-2 | 23-27 | 30-3 | 6-10 | 13-17 | 20-24 | 27-1 | 4-8 | 11-15 | 18-22 | 25-29 | 1-5 | 8-12 | 15-19 | 22-26 | 29-2
Edit tasks to reflect your departments and activities. Add or remove rows as needed. | Enter the name or names of employees in charge of completion. |  | Legend
|  |  | Est. completion time (incl. lead time) | [7 empty] | In Progress | [7 empty] | Completed | [8 empty] | Overdue
Dept. Information requests |  |  | Timelines are estimates from experienced sustainability reporters. Edit them as needed for your organization.
Human Resources | Enter name | Not started
Learning & Development | Enter name | Not started
Finance and tax | Enter name | Not started
Legal and Compliance | Enter name | Not started
Procurement/Sourcing | Enter name | Not started
Communications (stories, awards) | Enter name | Not started
Occupational Safety | Enter name | Not started
IT-Data Privacy | Enter name | Not started
Board of directors data | Enter name | Not started
Ops - initiatives data | Enter name | Not started
General Disclosures
Draft CEO statement | Enter name | Not started
CEO statement review | Enter name | Not started
Write general disclosures | Enter name | Not started
Obtain quotes/images | Enter name | Not started
Review materiality assessment | Enter name | Not started
Data collection and analysis
Obtain internal environmental data | Enter name | Not started
Data quality checks | Enter name | Not started
Obtain 3rd party data | Enter name | Not started
Calculations and analysis | Enter name | Not started
Emissions inventory | Enter name | Not started
Content
Write material disclosures | Enter name | Not started
Copy editing | Enter name | Not started
Prepare graphs and charts | Enter name | Not started
Design
Employee/executive images | Enter name | Not started
Report template and layout | Enter name | Not started
GRI Index | Enter name | Not started
Graphs and charts | Enter name | Not started
Figures, infographics | Enter name | Not started
Stock images | Enter name | Not started
Review
Legal review | Enter name | Not started
Post-audit finance review (if applicable) | Enter name | Not started
Executive review | Enter name | Not started
Corp Comm review | Enter name | Not started
Sustainability final fact check | Enter name | Not started
Distribution
Internal | Enter name | Not started
External | Enter name | Not started
GRI notification | Enter name | Not started

## Codes (hidden)
Status
Not started
In progress
Complete
Overdue
Cancelled