## ESG Project Plan Template (Part
*Workiva Solutions Architects will also provide delivery oversight (at least 12 hours per implementation)
|  |  | Partner | Workiva | Client | Dependency | Resources | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34
Stage 1 | Align |  | Lead role | Support* | Lead role |  |  | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20
Milestone | 1.1. Opportunity Won
| 1.1.1 | Engagement letter or SOW are signed | Partner contracting
| 1.1.2 | Resourcing assigns relevant resources (Project manager, build experts, ESG SMEs, etc) | Partner resourcing
| 1.2. Knowledge Transfer |  |  |  |  | 1.1 Completed
| 1.2.1. | Share documentation used during pre-sales (slides, notes, scoping, etc.) | Partner team
| 1.2.2. | Internal Sync with Workiva team (to potentialy include Seller, SE, & CSM) | Partner team
| 1.3.1 | CSM, Sales and Partner team to prepare Welcome Call deck | Partner team
Milestone | 1.4. Welcome Call with client |  |  |  |  | 1.3 Completed
Deliverable | 1.4.1. | Walk client through welcome deck | Partner PM | CSM |  |  | Welcome Deck
| 1.4.2. | Discuss source documentation PBC list with Client | Partner PM
| 1.4.3. | Discuss/schedule Weekly Project Status Calls with Client | Partner PM |  |  |  | Status Call Template
| 1.4.4. | Discuss/schedule Discovery Calls with Client | Partner PM
| 1.4.5. | Request list of workspace admins and initial users to add to workspace | Partner PM | CSM
| 1.5. Post-welcome call actions |  |  |  |  | 1.4 Completed
Deliverable | 1.5.1. | Follow-up email with call / meeting schedule summary | Partner PM
| 1.5.2. | Share source documentation PBC list with Client | Partner PM |  |  |  | PBC Checklist
| 1.5.2. | Add users Client Account and Workspace | NA-Workiva CSM | CSM
Deliverable | 1.5.3. | Prepare and share draft project plan | Partner PM
| 1.5.4. | Assign users to relevant learning hub sessions | NA-Workiva CSM | CSM
Milestone | 1.6. Customer Delivery of Documents (dependent on scope)
Deliverable | 1.6.1. | ESG Report
Deliverable | 1.6.2. | Data collection templates and source documentation
Deliverable | 1.6.3 | ESG Framework mappings and questionnaires
1.7. Schedule training sessions
| 1.7.1. | Schedule training sessions | NA-Workiva CSM | CSM
|  | Workspace Admin Training | NA-Workiva CSM | CSM
|  | Document Training | NA-Workiva CSM | CSM
|  | Process Admin Training | NA-Workiva CSM | CSM
|  | Data Approver Training | NA-Workiva CSM | CSM
|  | Data Provider Training | NA-Workiva CSM | CSM
1.8 Kick off call
| 1.8.1 | Schedule Kick off call | Partner PM
| 1.8.2 | Kick Off documentation (Kick Off deck, Files request list, Discovery questions) | Partner Build expert
| 1.8.3 | Schedule discovery sessions | Partner PM
| 1.8.4 | Planning call (Project Plan, Project Status Report) | Partner PM
Stage 2 | Discover
| Discovery sessions below can be scheduled as separate session or combined. This will depend on client avaiablity and project planning. Relevant materials to the discovery sessions will need to be received by the Workiva project team at least 3 days prior to the discovery session. |  |  |  |  | 1.5.2.Completed and received back completed | PBC Checklist
Milestone | 2.1. Discovery session 1 - Requirements & Future State | [5 empty] | Discovery deck
Dependency | 2.1.1. | Discuss project planning and priorities | Partner PM
| 2.1.2. | Present future state | Partner Build expert
| 2.1.3. | Recap and validate requirements (build + documentation) | Partner Build expert
| 2.1.4. | Summary recap email to client | Partner PM
Milestone | 2.2. Discovery session 2 - ESG Report Outputs |  |  |  |  | 1.6.1. | Discovery deck
| 2.2.1. | Provide relevant source documentation and files for output reports (e.g. prior year's versions of the report in editable format - docx, brand guidelines, style guide etc.) |  |  | Report lead |  | PBC Checklist
| 2.2.2. | Discuss and agree on output report setup approach | Partner Build expert |  | Report lead |  | ESG Report setup guide
| 2.2.3. | Discuss and agree on Design needs, InDesign process - Call with Design Agency | Partner PM | CSM | Design Agency
| 2.3.4. | Update planning in draft project plan to reflect agreed on approach | Partner PM
| 2.3.5. | Summary recap email to client | Partner Build expert
Milestone | 2.3. Discovery session 3 - ESG Data Collection Templates |  |  |  |  | 1.6.2. | Discovery deck
| 2.3.1 | Provide relevant source documentation and files for data collection (e.g. existing data collection sheets, data owner/approver overviews) |  |  | DC Lead |  | PBC Checklist
| 2.3.2. | Discuss and agree on data collection template approach | Partner Build expert
| 2.3.3. | Discuss and agree on data collection status tracking approach | Partner Build expert
| 2.3.4. | Update planning in draft project plan to reflect agreed on approach | Partner PM
| 2.3.5. | Summary recap email to client | Partner Build expert
Milestone | 2.4. Discovery session 4 - ESG Frameworks / Questionnaires |  |  |  |  | 1.6.3 | Discovery deck
| 2.4.1. | Provide relevant source documentation and files for framework/questionnaire management (e.g. existing framework outputs, framework mapping spreadsheets) |  |  | Frameworks Lead |  | PBC Checklist
| 2.4.2. | Discuss and agree on framework management approach | Partner Build expert
| 2.4.3. | Discuss and agree on future framework extensions and expansions approach | Partner Build expert
| 2.4.4. | Discuss and agree on data model for detailed ESG performance indicators in central factbook | Partner Build expert
| 2.4.5. | Update planning in draft project plan to reflect agreed on approach | Partner PM
| 2.4.6. | Summary recap email to client | Partner Build expert
Milestone | 2.5. Discovery session 5 - ESG Source system connections |  |  |  |  | 1.6.2. | Discovery deck
| 2.5.1. | Provide relevant information for source system connections that are in scope of the project (e.g. system name, data reports in scope for this system). Client is responsible for bringing the right skills / people to this call |  |  | Integration lead |  | PBC Checklist
| 2.5.2. | Discuss connection options, planning and phasing | Partner Build expert
| 2.5.3. | Share guides and other resource with client + discuss support model | Partner Build expert
| 2.5.4. | Update planning in draft project plan to reflect agreed on approach | Partner PM
| 2.5.5. | Summary recap email to client | Partner Build expert
Stage 3 | Design
Validation session related to each component can be scheduled separately or as a combined session. This will depend on client availability and project planning.
| 3.1. ESG Report Outputs | [5 empty] | Implementation guide
| 3.1.1. | Build example of ESG output report 1 based on client provided files | Partner Build expert |  |  | 2.2. Discovery session 2 - ESG Report Outputs
| 3.1.2. | Set up example style guide in report 1 example based on client provided files | Partner Build expert |  |  | 2.2. Discovery session 2 - ESG Report Outputs
| 3.1.3. | Validation session on document setup with client + client signoff | Partner Build expert |  | Report lead
Duplicate steps above if more than 1 output report is in scope
| 3.2. ESG Data Collection Templates | [5 empty] | Implementation guide
| 3.2.1. | Set up client provided files in Standard ESG Data Model sample (i.e. a handful indicators) | Partner Build expert |  |  | 2.3. Discovery session 3 - ESG Data Collection Templates
| 3.2.2. | Set up status tracking for this sample with dummy data providers | Partner Build expert |  |  | 2.3. Discovery session 3 - ESG Data Collection Templates
| 3.2.3. | Validation session on data collection with client + client signoff | Partner Build expert |  | DC lead
| 3.3. ESG Frameworks / Questionnaires | [5 empty] | Implementation guide
| 3.3.1. | Set up framework mapping Spreadsheet with client provided content sample | Partner Build expert |  |  | 2.4. Discovery session 4 - ESG Frameworks / Questionnaires
| 3.3.2. | Set up framework output Spreadsheets based on client provided content sample | Partner Build expert |  |  | 2.4. Discovery session 4 - ESG Frameworks / Questionnaires
| 3.3.3. | Set up central factbook with example of detailed performance indicators | Partner Build expert |  |  | 2.4. Discovery session 4 - ESG Frameworks / Questionnaires
| 3.3.4. | Validation session on frameworks with client + client signoff | Partner Build expert |  | Frameworks lead
| 3.4. ESG Source system connections | [5 empty] | Implementation guide
Milestone - Proof of concept Delivery? | 3.4.1. | Check in with client IT team on ESG source system connection(s) |  |  | Integration lead
Stage 4 | Build
Milestone | 4.1. ESG Report Outputs | [5 empty] | Implementation guide
| 4.1.1. | Full build of ESG output report 1 based on agreed design | Partner Build expert |  |  | 3.1.3.
| 4.1.2. | Full setup of style guide in report 1 based on agreed design | Partner Build expert |  |  | 3.1.3.
| 4.1.3. | Client project training on Workiva Documents | NA-Workiva CSM | CSM | Report lead | 4.1.1.
Deliverable | 4.1.4. | Handover of ESG output report to client | Partner Build expert |  | Report lead | 4.1.1., 4.1.2.
| 4.1.5. | Client third-party copywriter training on Workiva Documents | NA-Workiva CSM | CSM | Copywriters | 4.1.4.
| 4.1.6. | Third-party design partner training on Workiva Documents / designed reporting | NA-Workiva CSM | CSM | Design agency | 4.1.4.
Milestone | 4.2. ESG Data Collection Templates | [5 empty] | Implementation guide
| 4.2.1. | Full build out of all data collection templates in scope based on agreed design | Partner Build expert |  |  | 3.2.3.
| 4.2.2. | Full build out of status tracking for all data collection templates | Partner Build expert |  |  | 3.2.3.
Deliverable | 4.2.3. | Handover of Data Collection process to client | Partner Build expert | CSM | DC lead | 4.2.1., 4.2.2.
| 4.2.4. | Process Admin Training | Partner Build expert | CSM | DC lead | 4.2.3.
| 4.2.5. | Data Approver Training | Partner Build expert | CSM | DC lead | 4.2.3.
| 4.2.6. | Data Provider Training | Partner Build expert | CSM | DC lead | 4.2.3.
Milestone | 4.3. ESG Frameworks / Questionnaires | [5 empty] | Implementation guide
| 4.3.1. | Full build of framework mapping Spreadsheet based on agreed design | Partner Build expert |  |  | 3.3.4.
| 4.3.2. | Full build of framework output Spreadsheets based on client provided content sample | Partner Build expert |  |  | 3.3.4.
| 4.3.3. | Full build central factbook with detailed performance indicators | Partner Build expert |  | DC lead | 3.3.4.
| 4.3.4. | Connect framework outputs and central factbook to report outputs by means of linking | Partner Build expert |  | DC lead
Deliverable | 4.3.5. | Handover of Framework management process to client | Partner Build expert | CSM | DC lead | 4.3.1., 4.3.2., 4.3.3.
| 4.3.6. | Data model training | Partner Build expert | CSM | DC lead | 4.3.5.
| 4.4. ESG Source system connections | [5 empty] | Implementation guide
| 4.4.1. | Full build out of source system connection | Partner Build expert |  | Integration lead | 3.4.1.
| 4.4.2. | Connection of output report to ESG data model | Partner Build expert |  | Integration lead
Stage 5 | Enable
Milestone | 5.1. Testing and Signoff
| 5.1.1. | Final UAT session of complete build | Partner Build expert |  | ESG lead | 4.1.4., 4.2.3., 4.3.5., 4.4.1.
Room for intermediary UAT sessions
5.2. End-user training
| 5.2.1. | Training all end-users of Workiva platform | NA-Workiva CSM | CSM
5.3. Documentation
Deliverable | 5.3.1. | Data model documentation (custom) | Partner Build expert
Deliverable | 5.3.2. | Roll-forward documentation | Partner Build expert
Project Completion
Milestone | 6.1. Go-live
| 6.1.1 | Transition of support to Customer Success Manager | Partner PM | CSM
Color code key
Workiva responsible/lead
Workiva support/input
Client responsible/lead
Client support/input